## Sheet1
CMPUT301F15T05
Release Planning
Project Part | Use Case | Related User Stories
Project Part 4
2018-03-07 | 1. Post new task | US01.01.01, US01.01.02, US01.01.03
2018-03-07 | 2. View list of requester's task | US01.02.01
2018-03-07 | 3. Edit task | US01.03.01
2018-03-08 | 4. Delete task | US01.04.01
2018-03-08 | 5. View details of task | US02.01.01, US02.02.01
2018-03-08 | 6. Search for task | US04.01.01, US04.02.01
2018-03-19 | 7. Make a bid | US05.01.01
2018-03-17 | 8. View list of tasks that provider has bidded on | US05.02.01
2018-03-17 | 12. View assigned task for provider | US06.01.01
2018-03-17 | 13. View list of assigned task for requester | US06.02.01
2018-03-18 | 14. View geolocation for task on map | US10.02.01
2018-03-18 | 16. Make profile | US03.01.01
2018-03-18 | 17. Edit contact information | US03.02.01
2018-03-19 | 18. Offline behaviour | US08.01.01
2018-03-17 | 19. Access user profile | US03.03.01
2018-03-17 | 20. User has password and username to sign in | Wow factor 1
2018-03-18 | 21. Requester provides expected bid | Wow factor 2
2018-03-07 | 27. Read location and display on the map | part of US10.03.01
Project Part 5
| 22. Notify requester of a bid | US05.03.01
| 23. Decline a bid | US05.07.01
| 24. Set complete status of task | US07.01.01
| 25. Attach photo to task | US09.01.01
2018-03-24 | 26. View attached photo | US09.01.01
| 27. Set geolocation of task | US10.01.01
| 28. Provider can see all requesting tasks on map | Wow factor 3
| 29. Provider can filter requesting tasks by keyword | Wow factor 4
| 15. View tasks on map with location within 5km | US10.03.01
| 11. Accept bid | US05.06.01
| 9. View bidded task of requester | US05.04.01
2018-03-25 | 10. View bid on 1 task for requester | US05.05.01